## Summary
QAON11 GRUPA 2
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 143
| Number of testers | 6
| Test cycle duration | 7 days
Overall status
| Number of test cases planned | 105
| Number of test cases executed | 143
| Number of defects encountered so far | 65
| Number of critical defects | 18
| Critical defects percentage | 27.69%

## Detailed status
Number | Scenarios | Sub Levels | Priority | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Status (passed/failed) Mobile | Status (passed/failed) Tablet | Status (passed/failed) Desktop | Defect ID- Brief description | Severity
Unauthorized user
1 | Google authorization | ”Google” button | High | Cristiana | 2024-09-10 | Fail |  |  |  | Unable to log in using Google account ID: 66, 65, 64 | Major
2 | Form authentication | ”LOG IN” button | High | Georgiana (M) / Filip (T) / Catalina (D) | 11 - 14.09.2024 | Pass
3 |  | ”REGISTRATION” button | High | Georgiana (M) / Filip (T) / Catalina (D) | 11 - 14.09.2024 | Pass
4 |  | Email address validation | High | Georgiana (M) / Filip (T) / Catalina (D) | 11 - 14.09.2024 | Pass
5 |  | Password validation | High | Georgiana (M) / Filip (T) / Catalina (D) | 11 - 14.09.2024 | Pass
6 |  | Invalid values ​​for password and email | High | Georgiana (M) / Filip (T) / Catalina (D) | 11 - 14.09.2024 | Fail |  |  |  | Id 87,88, 74, 75, 76, 77, 78 | Major
7 | Authorized user | Page refresh | High | Cristiana | 2024-09-16 | Blocked |  |  |  | Refreshing the app on the Tablet, Mobile, Web results in a 404 error. ID: 58, 59, 60 | Blocker
8 | Header | Application logo | Medium | Vlad (M) / Vlad (T) / Bogdan (D) | 11-13.09/2024 | Pass
9 |  | Light mode/dark mode | High | Georgiana | 6689311 | Fail |  |  |  | 82 | Major
10 |  | Language change | High | Bogdan | 2024-09-16 | Fail/Pass/Pass |  |  |  | ID 70 | Minor
11 |  | Custom icon | Low | Vlad (M) / Vlad (T) / Bogdan (D) | 11-13.09/2024 | Pass
12 |  | ”Exit” button | Medium | Vlad (M) / Vlad (T) / Bogdan (D) | 11-13.09/2024 | Pass
13 | Home page | The message of the first authentication | Low | Cristiana | 2024-09-13 | Pass
14 |  | ”Balance” field | High | Cristiana | 2024-09-13 | Fail |  |  |  | Balance field can't be updated after the first login on the page ID:61, 62, 63 | Major
15 |  | Current date | High | Cristiana | 2024-09-13 | Pass
16 |  | Date change | High | Catalina | 11 - 14.09.2024 | Fail |  |  |  | Id 96 | Major
17 |  | ”Product description” field | Low | Filip | 2024-09-12 | Pass |  |  |  | - | -
18 |  | Invalid values for "Product description" field | Medium | Filip | 2024-09-13 | Fail |  |  |  | 35, 36, 37 | Low
19 |  | ”Product category” field | Medium | Filip | 2024-09-13 | Pass |  |  |  | - | -
20 |  | Transaction field | High | Filip | 2024-09-13 | Fail |  |  |  | ID 71, 72, 73 | Major
21 |  | ”Input” button | High | Bogdan | 2024-09-13 | Fail/Pass/Pass |  |  |  | ID 42, 43 | Minor
22 |  | ”Clear” button | Medium | Bogdan | 2024-09-14 | Fail |  |  |  | ID 38, 39, 40, 41, 49, 54 | Trivial/ Major
23 |  | Delete a transaction | Medium | Bogdan | 2024-09-13 | Pass
24 |  | The actions allowed by the date`s change | High | Catalina | 11 - 14.09.2024 | Fail |  |  |  | Id 89,90,92,93,94, 95 | Major
25 |  | The modal window activated by delete button | High | Vlad | 2024-09-11 | Fail |  |  |  | 28,29,30 | Major
26 |  | The actions that occurred after the deletion of a transaction | High | Vlad | 2024-09-11 | Pass
27 |  | Switch between ”Expenses” and ”Income” buttons | Hight | Georgiana | 6689308 | Pass
28 |  | Uses of the scroll | High | Catalina | 11 - 14.09.2024 | Pass/Fail/Fail |  |  |  | Id 84,85 | Major
29 |  | The ”Summary” box | High | Bogdan | 2024-09-13 | Fail |  |  |  | ID 31, 32, 33, 34, 55, 67, 68, 69 | Major/ Minor
30 |  | ”Reports” button | High | Bogdan | 2024-09-11 | Pass
31 | Reports page | ”Main page” button | Hight | Georgiana | 2024-09-13 | Pass
32 |  | ”Current period” button | Medium | Bogdan | 2024-09-12 | Pass
33 |  | ”Expenses” and ”Income” buttons | Medium | Filip | 2024-09-13 | Pass |  |  |  | - | -
34 |  | Transaction categories | High | Cristiana | 2024-09-13 | Pass
35 |  | Each transaction category has a graph | High | Vlad | 2024-09-11 | Fail |  |  |  | 25,26,27 | Major

## Bug report
Defect ID | Defect Description | Steps to reproduce | Priority | Mobile | Tablet | Desktop | State | Severity | Created by | Assigned to
96 | The user can add a transaction for a future day, although he should not be able to | 1.Click on the date. 2.Choose a future day. 3.Add a transaction: complete the ”Product description” field, choose a value from the ”Product category” field, add an amount in the corresponding field and then press the ”Input” button. | 1- High | 96 | 96 | 96 | Assigned | Major | Velicu Catalina | Velicu Catalina
90,93,95 | After the user adds a transaction, the user cannot see the added transaction nor the list of transactions of the future day | 1.Click on the date. 2.Choose a future day. 3.Add a transaction: complete the ”Product description” field, choose a value from the ”Product category” field, add an amount in the corresponding field and then press the ”Input” button. | 1- High | id 90 | id 93 | id 95 | Assigned | Major | Velicu Catalina | Velicu Catalina
89,92,94 | After the user adds a transaction, the user cannot see the added transaction nor the list of transactions of the previous day | 1.Click on the date and choose a previous day. 2.Add a transaction. Choose ”Expenses” or ”Income” button. Complete the ”Product description” field, choose a value from the ”Product category” field, add an amount in the corresponding field and then press the ”Input” button. | 1- High | id 89 | id 92 | id 94 | Assigned | Major | Velicu Catalina | Velicu Catalina
88 | The user must be informed that the email address has a maximum number of characters | 1.Enter a valid email address: fill in the ”Email” field with 64 characters. | 1- High |  |  | id 88 | Assigned | Major | Velicu Catalina | Velicu Catalina
87 | The user must be informed that the email address has a minimum number of characters | 1.Enter a valid email address: fill in the ”Email” field with 9 characters. | 1- High |  |  | id 87 | Assigned | Major | Velicu Catalina | Velicu Catalina
84.85 | The scroll does not work | 1.Click on the date and choose the desired day. 2.Add a transaction. 3.If more transactions are entered than the list of transactions can hold, use the scroll to navigate through the list. | 1- High |  | id 85 | id 84 | Assigned | Major | Velicu Catalina | Velicu Catalina
82 | The application's dark mode no longer leaves the logo fully visible. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.The user enters his account and is on the main page 3.The user uses the toggle box to switch to dark mode | 1- High | id 82 | id 82 | id 82 | Assigned | Major | Georgiana Mitica | Georgiana Mitica
74,75,76,77,78 | Invalid values for password and e-mail (tablet) - Write an email address with less than 10 characters Write an email address with more than 63 characters Write an email address with 1 character before "@" write an email starting with a hyphen Write an invalid password in the password field | 1.Write an email address with less than 10 characters 2.Write an email address with more than 63 characters 3.Write an email address with 1 character before "@" 4.write an email starting with a hyphen 5.Write an invalid password in the password field ( password only containing special characters ) | 2- Medium |  | 74, 75, 76, 77, 78 |  | Assigned | Moderate | Savu Filip | Savu Filip
71,72,73 | Transaction field - Transaction amount field is mandatory and only accepts values equal to or greater than 1. | 1.Enter a value with decimals 2.Press INPUT button | 1- High | 71 | 72 | 73 | Assigned | Major | Savu Filip | Savu Filip
70 | Product category info listed in Ukrainian instead of English on smartphone | 1.The app language is set to English by default 2.Scroll down to the Transactions summary section | 3-Low | 70 | 70 | 70 | Assigned | Minor | Bogdan Ardelean | Bogdan Ardelean
69 | Missing EXPENSES summary box on smartphone | 1.Scroll down to the bottom of the app’s main page. | 2- Medium | 69 | 69 | 69 | Assigned | Minor | Bogdan Ardelean | Bogdan Ardelean
68 | Incorrect display of registered Expenses transactions on smartphone | 1.Tap on the EXPENSES button | 3-Low | 68 | 68 | 68 | Assgned | Minor | Bogdan Ardelean | Bogdan Ardelean
67 | Missing INCOME summary box on smartphone | 1.Scroll down to the bottom of the app’s main page. | 2- Medium | 67 | 67 | 67 | Assigned | Minor | Bogdan Ardelean | Bogdan Ardelean
64,65,66 | Unable to log in using Google account | 1.Tap on the "Google" button to log in using a Google account. Is located on the top of the login form. 2.Select an active Google account on the Google login page. 3.Tap on the "Continue" button after selecting the Google account. 4.Observe that the login fails, and the user is redirected to an error page | 1- High | 66 | 65 | 64 | Assgned | Major | Cristiana Constantin | Cristiana Constantin
61,62,63 | Balance field can't be updated after the first log in on the page | 1.Go to “Balance“ and click on the input field, which is located at the top of the page. 2.Try to add a positive value. 3.Click on the “CONFIRM“ button. | 2- Medium | 63 | 62 | 61 | Assgned | Moderate | Cristiana Constantin | Cristiana Constantin
58,59,60 | Refreshing the web page results in a 404 error | 1.Navigate to any page (e.g., Reports, Transactions…). 2.Press the browser's refresh button or use the F5 key. 4.Observe the 404 error page. | 1- High | 60 | 59 | 58 | Assgned | Blocker | Cristiana Constantin | Cristiana Constantin
56 | Password created with symbols. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on password input field 3.Insert the password (“&('“!+;?,)§“) | 3-Low | 56 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
55 | Incorrect display of registered Income transactions on smartphone | 1.Tap on the INCOME button | 3-Low | 55 | 55 | 55 | Assgned | Minor | Bogdan Ardelean | Bogdan Ardelean
54 | Date field missing from the INCOME transaction registration form on smartphone | 1.In the Date field, select a different date than the current one and tap on the Income button located in the bottom right corner of the page 2.In the Income page, fill out the Product description, Product category and Transaction sum fields with valid values 3Tap the CLEAR button | 1- High | 54 | 54 | 54 | Assgned | Major | Bogdan Ardelean | Bogdan Ardelean
53 | Password created with only the "space" key. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on password input field 3.Insert the password (“ “) | 2- Medium | id 53 |  |  | Assigned | Moderate | Georgiana Mitica | Georgiana Mitica
52 | Password with symbols and "space". | 1.ccess the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on password input field 3.Insert the password (“#:,. !)&) | 3-Low | id 52 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
51 | Email address with random numbers written in the domain between "@" and ".". | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address (“rabdare@1.b”) | 1- High | id 51 |  |  | Assigned | Major | Georgiana Mitica | Georgiana Mitica
50 | Email address with random letters written in the domain. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address (“rabdare@a.b”) | 1- High | id 50 |  |  | Assigned | Major | Georgiana Mitica | Georgiana Mitica
49 | Date field missing from the EXPENSES transaction registration form on smartphone | 1.In the Date field, select a different date than the current one and tap on the Expenses button located in the bottom left corner of the page 2.In the Expenses page, fill out the Product description, Product category and Transaction sum fields with valid values 3.Tap the CLEAR button | 1- High | 49 | 49 | 49 | Assgned | Major | Bogdan Ardelean | Bogdan Ardelean
48 | Email address with the symbol "-" at the beginning. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field(-@yahoo.com) | 3-Low | id 48 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
47 | Email address with 1 single character before the @ symbol. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address (A@yahoo.com) | 3-Low | id 47 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
46 | Email address with less than 10 characters. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address (“s@1.c”) | 3-Low | id 46 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
45 | Email address created with more than 63 characters. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address | 3-Low | id 45 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
44 | Email address with "." at the username. | 1.Access the web application ( https://kapusta-qa-ro.p.goit.global/transactions/expenses ) 2.Tab on email address input field 3.Insert the email address (.rabdare@yahoo.com, rabdare.@yahoo.com) | 3-Low | id 44 |  |  | Assigned | Minor | Georgiana Mitica | Georgiana Mitica
43 | The INCOME monthly summary box is missing from layout on smartphone | 1.Tap on the INCOME button located in the bottom right side corner of the main page 2.In the Income transactions page, add a product description, select a product category and insert the transaction sum 3.Tap the INPUT button | 3-Low | 43 | 43 | 43 | Assgned | Minor | Bogdan Ardelean | Bogdan Ardelean
42 | The EXPENSES monthly summary box is missing from layout on smartphone | 1.Tap on the EXPENSES button located in the bottom left side corner of the main page 2.In the Expenses transactions page, add a product description, select a product category and insert the transaction sum 3.Tap the INPUT button | 3-Low | 42 | 42 | 42 | Assgned | Minor | Bogdan Ardelean | Bogdan Ardelean
39.41 | The date field is reset when clearing data for an Income transaction | 1.Click on the INCOME tab 2.In the Transaction input form, select a different date than the current one 3.Fill out the Product description, Product category and Transaction sun fields with valid values 4.Click the CLEAR button | 3-Low | 41 | 41 | 39 | Assgned | Trivial | Bogdan Ardelean | Bogdan Ardelean
38,40, | The date field is reset when clearing data for an Expense transaction | 1.Click on the EXPENSES tab 2.In the Transaction input form, select a different date than the current one 3.Fill out the Product description, Product category and Transaction sum fields with valid values 4.Click the CLEAR button | 3-Low |  | 40 | 38 | Assgned | Trivial | Bogdan Ardelean | Bogdan Ardelean
35,36,37 | Invalid values for product description field | 1.Enter a description with 1 character in the Product description field, (same result for more than 20 charaters) 2.Press INPUT button | 2- Medium | 37 | 36 | 35 | Assgned | Minor | Savu Filip | Savu Filip
32.34 | The EXPENSES transactions summary list is not displayed on tablet | 1.Tap on the EXPENSES tab | 2- Medium |  | 34 | 32 | Assgned | Major | Bogdan Ardelean | Bogdan Ardelean
31.33 | The INCOME transactions summary list is not displayed on tablet | 1.Tap on the INCOME tab | 2- Medium |  | 33 | 31 | Assgned | Major | Bogdan Ardelean | Bogdan Ardelean
28,29,30 | The modal window activated by delete button | 1.From Home page scroll down to transactions 2.Press delete button to delete an entry | 1- High | 28 | 30 | 29 | Assgned | Major | Vlad Mihalcea | Vlad Mihalcea
25,26,27 | Each transaction category has a graph | 1.From Home page go to Reports 2.In reports page select a category 3.After selecting category verify graph | 1- High | 26 | 25 | 27 | Assgned | Major | Vlad Mihalcea | Vlad Mihalcea